| 40464 | Coordinate a planned operational outage for a complex energy and chemical plant |
| --- | --- |

| Kaupae ¦ Level | 5 |
| --- | --- |
| Whiwhinga ¦ Credit | 30 |
| Whāinga ¦ Purpose | This skill standard is intended for experienced personnel working in supervisory roles in a complex energy and chemical plant. People credited with this skill standard are able to: contribute to a plan for the outage; coordinate the operational shutdown and plant isolation; coordinate operational components during the execution of the outage plan; coordinate the commissioning and testing of equipment and plant; coordinate the plant handover and start-up; contribute to the outage debriefing; and evaluate own performance in coordinating operational components of the outage plan, in a complex energy and chemical plant. This skill standard can be used in the New Zealand Energy and Chemical qualifications at Level 5. |

Hua o te ako me Paearu aromatawai | Learning outcomes and assessment criteria

| Hua o te ako ¦ Learning outcomes | Paearu aromatawai ¦ Assessment criteria |
| --- | --- |
| - Contribute to a plan for the outage in a complex energy and chemical plant. | - Identify operational activities intended to be completed in the outage and collate information for the outage plan. |
|  | - Provide operational input into the management, performance, and implementation of the outage plan. |
|  | - Liaise with outage stakeholders to confirm operational aspects of the outage plan and collate information. |
|  | - Identify and resolve any conflicts arising in operational activities. |
|  | - Communicate the outage plan to outage stakeholders. |
| - Coordinate the operational shutdown and plant isolation in a complex energy and chemical plant. | - Monitor activities in the shutdown plan and take action to maintain the required progress. |
|  | - Monitor activities in the isolation plan and take action to ensure the safety of personnel and plant. |
|  | - Complete communication and reporting requirements for the shutdown and isolation plans. |
| - Coordinate operational components during the execution of the outage plan in a complex energy and chemical plant. | - Implement and monitor safe work management system requirements for the daily work plans to ensure a safe work environment. |
|  | - Review human and physical resources required for daily work plans and take action to ensure timely progress against the outage plan. |
|  | - Communicate progress of operational components and any amendments to the outage plan to outage stakeholders. |
| - Coordinate the commissioning and testing of equipment and plant in a complex energy and chemical plant. | - Review human and physical resource plans for commissioning and testing and take action to ensure scheduled activities are completed as planned. |
|  | - Implement and monitor safe work management system requirements for the scheduled commissioning and testing to ensure a safe work environment. |
|  | - Communicate and report commissioning and testing progress to outage stakeholders. |
| - Coordinate the plant handover and start-up in a complex energy and chemical plant. | - Confirm completion of the outage work plan with outage stakeholders. |
|  | - Complete operational acceptance of equipment. |
|  | - Monitor activities in the plant de-isolation plan and take action to ensure personnel and plant safety. |
|  | - Monitor activities in the pre-start and start-up plan and take action to maintain progress. |
|  | - Communicate and report progress of the start-up to outage stakeholders. |
| - Contribute to the outage debriefing in a complex energy and chemical plant. | - Analyse operational personnel, resource and timeframe overruns to determine the root cause. |
|  | - Communicate outcomes of the analysis to outage stakeholders. |
|  | - Recommend modifications to the methodology, tasks, activities, personnel, resources, timeframes and safe work management system to improve future outage planning. |
| - Evaluate own performance in coordinating operational components of the outage plan in a complex energy and chemical plant. | - Evaluate own performance reviewing actions and decisions in coordinating operational components of the outage plan. |
|  | - Analyse the outcomes of actions and decisions to determine what worked well and areas for improvement. |
|  | - Record recommendations for improvement in line with organisational requirements. |

Pārongo aromatawai me te taumata paearu | Assessment information and grade criteria

Assessment specifications:

- evidence for the practical components of this skill standard must be supplied from the workplace.

- evidence for all outcomes must be presented in accordance with organisational requirements.

- 1c: stakeholders include internal and external.

Definitions:

Complex energy and chemical plant – a plant that consists of multiple integrated processing units, interdependent systems, and advanced control mechanisms, requiring coordinated operations for safe and efficient production. Examples include petrochemical refineries, power generation facilities, large-scale dairy and meat processing plants, and other operations with significant process integration.

Energy and chemical plant may be in – petrochemical, agri-nutrient, power generation, dairy processing, meat processing, and wood fibre manufacturing, or other plants that operate with a combination of high temperatures, pressures, steam and/or chemicals in gas, liquid or solid form.

Organisational requirements – documented policies and procedures.  These may include: equipment manufacturers’ procedures; plant procedures; suppliers’ instructions; site signage; codes of practice; company health and safety plans; on site briefings; and supervisor’s instructions.  This includes all regulatory and legislative obligations that apply to the plant.

Outage – the planned shutdown and maintenance or inspection of equipment and plant and the re-establishment of plant operation.

Outage stakeholders – personnel in other parts of the plant that are involved or impacted by the outage, and external suppliers, contractors and customers.

Plant – the operational unit, equipment and/or workplace at which the person is working.

Ngā momo whiwhinga | Grades available

Achieved

Ihirangi waitohu | Indicative content

- Outage operational activities such as – shutdown equipment, isolations, housekeeping, equipment preparation, hand over, inspections, de-isolation, re-commissioning, testing, start-up.

- Operational activities information such as– activity timeframes, personnel requirements, materials, equipment, activity start conditions, other resources.

Rauemi | Resources

Legislation relevant to this skill standard includes but is not limited to:

- Hazardous Substances and New Organisms Act 1996;

- Health and Safety at Work Act 2015;

- Resource Management Act 1991;

and any subsequent amendments.

Pārongo Whakaū Kounga | Quality assurance information

| Ngā rōpū whakatau-paerewa ¦ Standard Setting Body | Hanga-Aro-Rau Manufacturing, Engineering and Logistics Workforce Development Council |
| --- | --- |
| Whakaritenga Rārangi Paetae Aromatawai ¦ DASS classification | Manufacturing > Energy and Chemical Plant > Operation of Energy and Chemical Plant |
| Ko te tohutoro ki ngā Whakaritenga i te Whakamanatanga me te Whakaōritenga ¦ CMR | 0079 |

| Hātepe ¦ Process | Putanga ¦ Version | Rā whakaputa ¦ Review Date | Rā whakamutunga mō te aromatawai ¦ Last date for assessment |
| --- | --- | --- | --- |
| Rēhitatanga ¦ Registration | 1 | 24 April 2025 | N/A |
| Kōrero whakakapinga ¦ Replacement information | This skill standard replaced unit standard 28165. |  |  |
| Rā arotake ¦ Planned review date | 31 December 2029 |  |  |

Please contact Hanga-Aro-Rau Manufacturing, Engineering and Logistics Workforce Development Council at qualifications@hangaarorau.nz to suggest changes to the content of this skill standard.