| Title | Plan aircraft maintenance activities using project management techniques |  |  |
| --- | --- | --- | --- |
| Level | 5 | Credits | 25 |

| Purpose | People credited with this unit standard are, for a planned aircraft maintenance activity, able to: establish work content; produce a production plan; consult with affected parties; and produce maintenance task documentation. |
| --- | --- |

| Classification | Aeronautical Engineering > Aeronautical Engineering Planning |
| --- | --- |

| Available grade | Achieved |
| --- | --- |

Guidance Information

1	All tasks must be carried out in accordance with enterprise procedures.

2	Definition

Enterprise procedures – procedures used by the organisation carrying out the work and applicable to the tasks being carried out.  Examples are – standard operating procedures, safety procedures, equipment operating procedures, codes of practice, quality management practices and standards, procedures to comply with legislative and local body requirements.

Outcomes and performance criteria

Outcome 1

Establish work content for a planned aircraft maintenance activity.

Performance criteria

1.1	Work content is verified from the maintenance specification and/or approved maintenance programme and matches work scope.

1.2	Special requirements applicable to the aircraft and/or enterprise are identified and added to the work content.

Range	Extended Range Operations (EROPS), Extended Twin Operations (ETOPS), staggered component changes, special inspections, concessions, deviations.

Outcome 2

Produce a production plan for a planned aircraft maintenance activity.

Performance criteria

2.1	Task requirements are determined in terms of resources, predecessors, and time to complete.

2.2	Resource constraints are identified in terms of quantity and availability.

2.3	Tasks are sequenced, using project management techniques to achieve required completion time.

Range	network diagram, Gantt chart, critical path, resource levelling.

2.4	Maintenance activity completion time is determined to meet requirements of customer and/or enterprise.

2.5	Production plan is produced and published.

Range	manually, by computer program.

Outcome 3

Consult with affected parties for a planned aircraft maintenance activity.

Performance criteria

3.1	Parties who are affected by the production plan are identified.

Range	production, support workshops, supply, technical services, quality control, customer.

3.2	Consultation with affected parties is carried out to obtain information needed to develop a production plan.

3.3	Consensus is obtained from affected parties for amendments to plan.

3.4	Final approval and/or agreement for the production plan is obtained from affected parties.

Outcome 4

Produce maintenance task documentation for a planned aircraft maintenance activity.

Range	routine work, non-routine work, modifications, special inspections, component changes.

Performance criteria

4.1	Maintenance task documents are produced.

4.2	Maintenance task documents are issued and controlled.

| Planned review date | 31 December 2027 |
| --- | --- |

Status information and last date for assessment for superseded versions

| Process | Version | Date | Last Date for Assessment |
| --- | --- | --- | --- |
| Registration | 1 | 23 July 1997 | 31 December 2016 |
| Revision | 2 | 8 May 2001 | 31 December 2016 |
| Review | 3 | 19 May 2006 | 31 December 2016 |
| Review | 4 | 22 August 2014 | 31 December 2021 |
| Review | 5 | 26 March 2020 | N/A |
| Rollover and Revision | 6 | 26 April 2024 | N/A |

| Consent and Moderation Requirements (CMR) reference | 0028 |
| --- | --- |

This CMR can be accessed at http://www.nzqa.govt.nz/framework/search/index.do.

Comments on this unit standard

Please contact Ringa Hora Services Workforce Development Council qualifications@ringahora.nz if you wish to suggest changes to the content of this unit standard.