| Title | Define and document the scope and requirements of a planned aircraft maintenance activity |  |  |
| --- | --- | --- | --- |
| Level | 5 | Credits | 45 |

| Purpose | People credited with this unit standard are, for a planned aircraft maintenance activity, able to: define work and human resource requirements; define spares, equipment, and facility requirements; and produce the documentation required. |
| --- | --- |

| Classification | Aeronautical Engineering > Aeronautical Engineering Planning |
| --- | --- |

| Available grade | Achieved |
| --- | --- |

Guidance Information

1	All tasks must be carried out in accordance with enterprise procedures.

2	Definitions

Enterprise procedures – procedures used by the organisation carrying out the work and applicable to the tasks being carried out.  Examples are – standard operating procedures, safety procedures, equipment operating procedures, codes of practice, quality management practices and standards, procedures to comply with legislative and local body requirements.

Human resource – the number and type of personnel required completing a task or series of tasks, and the expected time those personnel will be required.

3	Maintenance activity may include – routine work, defect rectification, special inspections, component changes, modifications on an aircraft or major component.

Outcomes and performance criteria

Outcome 1

Define work requirements for a planned aircraft maintenance activity.

Performance criteria

1.1	Extent of maintenance activity is established from, and consistent with, customer specifications.

1.2	Known work content is established in accordance with relevant documentation.

Range	maintenance schedules, specifications, logbooks, records, airworthiness authority requirements, technical directives, manufacturer requirements.

1.3	Recommended additional work which will produce maintenance efficiencies and/or cost savings is identified.

1.4	Estimated unscheduled work content is established in accordance with scheduled work and type of planned activity.

Range	work arising, rectifications.

Outcome 2

Define human resource requirements for a planned aircraft maintenance activity.

Performance criteria

2.1	Skill groups are identified in accordance with work requirements for the planned activity.

2.2	Human resource requirements are calculated in terms of identified skill groups.

2.3	Adjustments that allow for lost time are made to human resource requirements at a rate relevant to the planned activity.

2.4	Total human resource requirements are calculated, in accordance with known and estimated work content.

Outcome 3

Define spares requirements for a planned aircraft maintenance activity.

Performance criteria

3.1	Spares requirements are determined in accordance with known work content of planned activity.

Range	consumables, repairables, rotables.

3.2	Spares requirements are estimated and meet estimated unscheduled work content.

Outcome 4

Define equipment and facility requirements for a planned aircraft maintenance activity.

Performance criteria

4.1	Equipment requirements are established to meet work activities needs.

Range	specialist tooling, specialist docking, specialist lifting, specialist trestling.

4.2	Facility requirements are determined to meet work activities needs.

Range	hangar space, workshop space, support areas.

Outcome 5

Produce the documentation required for a planned aircraft maintenance activity.

Performance criteria

5.1	Work content and resources required are documented and presented.

Range	work scope, pre-maintenance survey.

5.2	Documentation is distributed.

| Planned review date | 31 December 2027 |
| --- | --- |

Status information and last date for assessment for superseded versions

| Process | Version | Date | Last Date for Assessment |
| --- | --- | --- | --- |
| Registration | 1 | 23 July 1997 | 31 December 2016 |
| Revision | 2 | 8 May 2001 | 31 December 2016 |
| Review | 3 | 19 May 2006 | 31 December 2016 |
| Review | 4 | 22 August 2014 | 31 December 2021 |
| Review | 5 | 26 March 2020 | N/A |
| Rollover and Revision | 6 | 26 April 2024 | N/A |

| Consent and Moderation Requirements (CMR) reference | 0028 |
| --- | --- |

This CMR can be accessed at http://www.nzqa.govt.nz/framework/search/index.do.

Comments on this unit standard

Please contact Ringa Hora Services Workforce Development Council qualifications@ringahora.nz if you wish to suggest changes to the content of this unit standard.