| Title | Plan and prepare for the erection of scaffolding |  |  |
| --- | --- | --- | --- |
| Level | 3 | Credits | 5 |

| Purpose | People credited with this unit standard are able to: – confirm the purpose, duty load and parameters of the scaffold to be erected; – notify the scaffold to be erected; – identify on-site hazards associated with the erection of the proposed scaffold and complete the required safety documentation; – sketch plans for the erection of the proposed scaffold; and – assess and schedule the transport of equipment necessary for the erection of the scaffold. |
| --- | --- |

| Classification | Lifting Equipment > Elementary Scaffolding |
| --- | --- |

| Available grade | Achieved |
| --- | --- |

Guidance Information

1	This unit standard has been developed for learning and assessment on-job or off-job in a simulated environment.  Where supervision is required by law, the supervisor must hold the appropriate Certificate of Competence for the scaffolding work undertaken.

2	All tasks are to be carried out in accordance with:

a	quality management systems;

b	designer’s requirements and manufacturers' operating instructions; legislation, regulations, bylaws, Health and Safety at Work Act 2015, and Health and Safety in Employment Regulations 1995;

c	the most up to date version of the Good Practice Guidelines – Scaffolding in New Zealand (GPG), 2016 available from https://www.worksafe.govt.nz/topic-and-industry/working-at-height/scaffolding-in-new-zealand/;

and all subsequent amendments and replacements.

3	Definitions

Hazards refer to those occurrences, processes, substances or situations as determined by the organisation that are an actual or potential cause or source of harm associated with, but not limited to: process, activities, environment, equipment, materials, work organisation, site and facilities.

Scaffolding is as defined in the GPG and in the Health and Safety in in Employment Regulations 1995.

Scaffold plan: A key design document prepared by the candidate and used as a basis for the erection of a particular scaffold.

4	Training and assessment

This unit standard is intended to cover the planning and preparation for erecting a scaffold, until the point of starting work on site.

Outcomes and performance criteria

Outcome 1

Confirm the purpose, duty load and parameters of the scaffold to be erected.

Performance criteria

1.1	Identify the purpose of the scaffold.

Range	may include but is not limited to – plans, consultation with supervisor, consultation with client.

1.2	Determine the duty load for the scaffold.

Range	may include but is not limited to – light, medium, heavy, special duty.

1.3	Confirm the parameters of the scaffold to be erected on site.

Range	at least dimensions of length, height and width.

Outcome 2

Notify the scaffold to be erected.

Range	may include but is not limited to – local authority, the Police (traffic services), electricity authorities, WorkSafe New Zealand.

Performance criteria

2.1	Determine whether a proposed scaffold needs to be notified.

2.2	Notify the scaffold to be erected.

Outcome 3

Identify on-site hazards associated with the erection of the proposed scaffold and complete the required safety documentation.

Performance criteria

3.1	Identify on-site hazards.

3.2	Complete the required workplace safety documentation in relation to the proposed scaffold.

Range	may include but is not limited to – traffic management plan, gear-drop site sketch.

Outcome 4

Sketch plans for the erection of the proposed scaffold.

Performance criteria

4.1	Draw a sketch plan of the proposed scaffolding in the context of the given site.

4.2	Establish the height of the required working platforms from the top down, and record the findings on the scaffolding plan.

4.3	Establish the height of the required base lift and record the findings on the scaffolding plan.

Range	must not exceed 3 metres.

4.4	Establish the intermediate lift heights and record the findings on the scaffolding plan.

Range	proprietary systems to manufacturer specifications, non-proprietary systems 1.8-2.1 metres.

Outcome 5

Assess and schedule the transport of equipment necessary for the erection of the scaffold.

Performance criteria

5.1	Compile an equipment list for the erection of the scaffold.

5.2	Schedule equipment for the erection of the scaffold.

5.3	Compile a loading priority list for the erection of the scaffold.

5.4	Schedule transport for the moving of equipment to the scaffold site.

| Replacement information | This unit standard, unit standard 20855, and unit standard 23228 replaced unit standard 4200 and unit standard 4202. |
| --- | --- |

| Planned review date | 31 December 2026 |
| --- | --- |

Status information and last date for assessment for superseded versions

| Process | Version | Date | Last Date for Assessment |
| --- | --- | --- | --- |
| Registration | 1 | 23 March 2006 | 31 December 2016 |
| Revision | 2 | 25 July 2007 | 31 December 2016 |
| Rollover and Revision | 3 | 20 June 2008 | 31 December 2016 |
| Review | 4 | 16 July 2015 | 31 December 2019 |
| Rollover and Revision | 5 | 23 November 2017 | 31 December 2025 |
| Review | 6 | 24 February 2022 | N/A |
| Revision | 7 | 24 August 2023 | N/A |

| Consent and Moderation Requirements (CMR) reference | 0003 |
| --- | --- |

This CMR can be accessed at http://www.nzqa.govt.nz/framework/search/index.do.

Comments on this unit standard

Please contact the Waihanga Ara Rau Construction and Infrastructure Workforce Development Council qualifications@waihangaararau.nz if you wish to suggest changes to the content of this unit standard.