| Title | Explain and plan project scope and control processes in a marine or composite project |  |  |
| --- | --- | --- | --- |
| Level | 6 | Credits | 12 |

| Purpose | People credited with this unit standard are able to explain the function and purpose of elements of the project definition; explain project control requirements and processes; and plan project scope and control processes in a marine or composite project. |
| --- | --- |

| Classification | Boating Industries > Boatbuilding |
| --- | --- |

| Available grade | Achieved |
| --- | --- |

Guidance Information

This unit standard is for internal project control and doesn’t cover legal or external contract management.

Outcomes and performance criteria

Outcome 1

Explain the function and purpose of elements of the project definition for a marine or composite project.

Performance criteria

1.1	The function and purpose of the build contract in relation to defining the project is explained.

1.2	The function and purpose of the build specification in relation to defining the project is explained.

1.3	The function and purpose of the build schedule in relation to defining the project is explained.

Outcome 2

Explain project control requirements and processes in a marine or composite project.

Performance criteria

2.1	Project control requirements and processes are explained in accordance with project control parameters.

Range	project control parameters – time, cost, scope, quality.

2.2	Project communication requirements and processes are explained in 	accordance with marine or composite project requirements.

Range	internal communication, external communication.

2.3	Requirements for change control are explained for situations where variations to build specifications are required.

2.4	Requirements for specification change control are explained in terms of potential time, scope, and cost ramifications.

2.5	Processes for monitoring and controlling specification changes are explained in accordance with a marine or composite contract.

Outcome 3

Plan project scope and control processes in a marine or composite project.

Performance criteria

3.1	Project scope and performance metrics are planned for a marine or composite project.

3.2	Control processes and strategies are planned in accordance with workplace policies and procedures.

| Planned review date | 31 December 2027 |
| --- | --- |

Status information and last date for assessment for superseded versions

| Process | Version | Date | Last Date for Assessment |
| --- | --- | --- | --- |
| Registration | 1 | 21 May 2010 | 31 December 2018 |
| Review | 2 | 17 August 2017 | 31 December 2024 |
| Review | 3 | 25 August 2022 | N/A |

| Consent and Moderation Requirements (CMR) reference | 0136 |
| --- | --- |

This CMR can be accessed at http://www.nzqa.govt.nz/framework/search/index.do.

Comments on this unit standard

Please contact Hanga-Aro-Rau Manufacturing, Engineering and Logistics Workforce Development Council qualifications@hangaarorau.nz if you wish to suggest changes to the content of this unit standard.