| Title | Carry out a work plan specific to own role for civil infrastructure works |  |  |
| --- | --- | --- | --- |
| Level | 4 | Credits | 10 |

| Purpose | People credited with this unit standard are able to carry out a work plan specific to own role for civil infrastructure works. |
| --- | --- |

| Classification | Infrastructure Works > Infrastructure Civil Works |
| --- | --- |

| Available grade | Achieved |
| --- | --- |

Guidance Information

1	Evidence presented for assessment against this unit standard must be consistent with safe working practices and be in accordance with relevant legislative and industry requirements.

2	Legislation relevant to this unit standard include: Health and Safety at Work Act 2015; and all subsequent amendments and replacements.

3	Definition

Industry requirements refer to relevant policies, processes, methodologies, industry codes of practice, site specific health and safety plans, standard operating procedures, site safety plans, quality plans, work plans, traffic management plans, contract work programmes, job safety analysis, safe work method statements, job instructions, manufacturer’s requirements, contract specifications, manuals, procedural documents.

Outcomes and performance criteria

Outcome 1

Carry out a work plan specific to own role for civil infrastructure works.

Performance criteria

1.1	Schedule and work sequences are discussed with site supervisor and confirmed in accordance with contract specifications.

1.2	Schedule is followed, and actions are taken to ensure milestones and critical outcomes are achieved on target.

1.3	Resources are monitored, and actions are taken to ensure their efficient use.

1.4	Progress against the plan is reviewed, and actions are taken to align progress with planned outcomes.

Range	slippage, contingencies, variations.

1.5	At the completion of the plan, any required corrective actions for the works are identified and carried out, and any reporting is completed in accordance with contract specifications.

| Planned review date | 31 December 2026 |
| --- | --- |

Status information and last date for assessment for superseded versions

| Process | Version | Date | Last Date for Assessment |
| --- | --- | --- | --- |
| Registration | 1 | 27 September 2018 | 31 December 2023 |
| Review | 2 | 29 July 2021 | N/A |

| Consent and Moderation Requirements (CMR) reference | 0101 |
| --- | --- |

This CMR can be accessed at http://www.nzqa.govt.nz/framework/search/index.do.

Comments on this unit standard

Please contact Connexis - Infrastructure Industry Training Organisation qualifications@connexis.org.nz if you wish to suggest changes to the content of this unit standard.