| Title | Describe and apply project management techniques to an improvement project in a dairy processing operation |  |  |
| --- | --- | --- | --- |
| Level | 5 | Credits | 20 |

| Purpose | People credited with this unit standard are able to: describe the project management delivery process; and apply project management techniques to an improvement project, in a dairy processing operation. |
| --- | --- |

| Classification | Dairy Processing > Milk Processing |
| --- | --- |

| Available grade | Achieved |
| --- | --- |

Guidance Information

1	Legislation relevant to this unit standard includes but is not limited to:

- Health and Safety at Work Act 2015;

2	All evidence presented in this unit standard must be in accordance with organisational requirements.

3	Definitions

Improvement project – a defined scope of work that focuses on improving a single or multiple process within a dairy processing operation.

Organisational requirements – instructions to staff on policies and procedures which are documented in memo or manual format and are available in the workplace. These requirements include but are not limited to – manufacturer specifications, company quality management requirements, site procedures, and legislative requirements.

4	For the purposes of assessment, the learner can apply knowledge of project management to a project working as a lead or within a team situation.

Outcomes and performance criteria

Outcome 1

Describe the project management delivery process in a dairy processing operation.

Performance criteria

1.1	Describe key organisational considerations in terms of the project management delivery process.

Range	considerations may include but are not limited to – time, scope, cost, internal resources, external resources;

evidence of three considerations is required.

1.2 	Describe the roles of key personnel in terms of the project management delivery process.

Range	key personnel may include but are not limited to – senior management, sponsor or budget manager, project manager, stakeholders, team members, suppliers;

evidence of four key personnel is required.

1.3 	Describe the stages of project management in terms of the delivery process.

Range	stages include but are not limited to – initiation, planning, implementation, monitoring, closeout.

1.4	Describe the use of project management tools in terms of the delivery process.

Range	tools may include but are not limited to – charter, stakeholder register, risk plan, budget, change management plan, communication protocols, resources, status report, close-out report, acceptance report, take-over report;

evidence of six tools is required.

Outcome 2

Apply project management techniques to an improvement project in a dairy processing operation.

Performance criteria

2.1 	Take actions to initiate an improvement project.

Range	actions may include but are not limited to – a statement of work, a business case, a project charter, authorisation to proceed;

evidence of two actions is required.

2.2 	Develop a project management plan to deliver a defined improvement outcome.

Range 	plan elements may include but are not limited to – sponsor, scope, aim, schedule, risk, stakeholders, resources, cost, quality, change management, communication;

evidence of five elements is required.

2.3 	Implement and monitor the project management delivery process to achieve the improvement project outcome.

2.4 	Prepare and circulate regular project status reports to stakeholders.

2.5 	Manage introduced change and unexpected delays to the improvement project plan, including informing and seeking stakeholder approval.

2.6 	Complete closure activities and documentation once the improvement project outcome has been delivered.

Range 	closure activities may include but are not limited to – finalising project activities, acceptance testing, takeover, outcome acceptance by sponsor and stakeholders;

evidence of three activities is required;

closure documentation may include but is not limited to – review of project outcomes against baseline requirements, deviations, ongoing support, ongoing maintenance requirements, final sign-off;

evidence of three items of closure documentation is required.

2.7	Complete a review of the improvement project delivery process to evaluate project successes, difficulties, learning and suggestions for further improvements.

| Planned review date | 31 December 2026 |
| --- | --- |

Status information and last date for assessment for superseded versions

| Process | Version | Date | Last Date for Assessment |
| --- | --- | --- | --- |
| Registration | 1 | 28 April 2022 | N/A |

| Consent and Moderation Requirements (CMR) reference | 0022 |
| --- | --- |

This CMR can be accessed at http://www.nzqa.govt.nz/framework/search/index.do.

Comments on this unit standard

Please contact Hanga-Aro-Rau Manufacturing, Engineering and Logistics Workforce Development Council qualifications@hangaarorau.nz if you wish to suggest changes to the content of this unit standard.